## Garage Automation
Task Name | Start | Finish | Duration | Assigned To | % Complete | Status | Predecessors
Web Site Design | 2017-02-19 | 2017-03-06 | 16d |  | 87% | In Progress
Create basic layout | 2017-02-19 | 2017-03-01 | 11d | Team 1,2,3 | 100% | Complete
Implement basic database queries | 2017-02-25 | 2017-03-01 | 5d | Team 1,2,3 | 100% | Complete
Create polished styling | 2017-03-01 | 2017-03-04 | 4d | Team 1,2,3 | 60% | At Risk
Implement smooth mobile rendering | 2017-03-01 | 2017-03-06 | 6d | Team 1,2,3 | 70% | At Risk
Math | 2017-02-19 | 2017-02-22 | 4d |  | 100% | Complete
Fine tune recommended spot alogrithm | 2017-02-19 | 2017-02-22 | 4d | Team 2 | 100% | Complete
Test and simulate it in MATLAB | 2017-02-22 | 2017-02-22 | 1d | Team 2 | 100% | Complete
Software Testing | 2017-03-05 | 2017-03-25 | 21d |  | 35% | In Progress
Test Design | 2017-03-05 | 2017-03-23 | 19d | Team 1,2,3 | 40% | In Progress
Design simulation | 2017-03-13 | 2017-03-23 | 11d | Team 1,2,3 | 25% | In Progress
Perform Tests | TBD | 2017-03-25 |  | Team 1,2,3 | 0% | In Progress
Record Results from Tests | TBD | 2017-03-25 |  | Team 1,2,3 | 0% | In Progress
Database Design | 2017-02-19 | 2017-03-09 | 19d |  | 100% | Complete
Determine user model attributes | 2017-02-19 | 2017-02-25 | 7d | Team 1,2,3 | 100% | Complete
Determine manager model atrributes | 2017-02-25 | 2017-02-25 | 1d | Team 1,2,3 | 100% | Complete
Determine the type of data stored | 2017-03-03 | 2017-03-03 | 1d | Team 1,2,3 | 100% | Complete
Determine which type of requests and how the data will be structured | 2017-03-09 | 2017-03-09 | 1d | Team 1,2,3 | 100% | Complete
Report 2 Part 1 | 2017-02-19 | 2017-02-26 | 8d |  | 100% | Complete
Interaction Diagrams | 2017-02-19 | 2017-02-26 | 8d | Team 3 | 100% | Complete
Report 2 Part 2 | 2017-02-19 | 2017-03-05 | 15d |  | 100% | Complete
Class Diagram | 2017-02-19 | 2017-03-04 | 14d | Gao, Guy, Peter | 100% | Complete
Data Types and Operation Signatures | 2017-02-26 | 2017-03-05 | 8d | Gao, Guy, Peter | 100% | Complete
Traceability Matrix | 2017-02-26 | 2017-03-05 | 8d | Arthur | 100% | Complete
Architectural Styles | 2017-02-26 | 2017-03-05 | 8d | Vatsal | 100% | Complete
Identifying Subsystems | 2017-02-26 | 2017-03-05 | 8d | Vatsal | 100% | Complete
Mapping Subsystems to Hardware | 2017-02-26 | 2017-03-05 | 8d | Guy | 100% | Complete
Persistent Data | 2017-02-26 | 2017-03-05 | 8d | Guy | 100% | Complete
Network Protocol | 2017-02-26 | 2017-03-05 | 8d | Kendric | 100% | Complete
Global Control Flow | 2017-02-26 | 2017-03-05 | 8d | Peter | 100% | Complete
Hardware Requirements | 2017-02-26 | 2017-03-05 | 8d | Kendric | 100% | Complete
Final Report 2 | 2017-03-05 | 2017-03-12 | 8d |  | 100% | Complete
Algorithms | 2017-03-05 | 2017-03-12 | 8d | Team 1, 2, and 3 | 100% | Complete
Data Structures | 2017-03-05 | 2017-03-12 | 8d | Team 1, 2, and 3 | 100% | Complete
Project Management | 2017-03-05 | 2017-03-12 | 8d | Vatsal | 100% | Complete
Demo 1 | 2017-03-12 | 2017-03-28 | 17d |  | 8% | In Progress
Product Brocure | 2017-03-12 | 2017-03-28 | 17d |  | 25% | In Progress
Prepare Slide Per Group | 2017-03-12 | 2017-03-28 | 17d |  | 0% | Not Started
Mock Demo | 2017-03-12 | 2017-03-28 | 17d |  | 0% | Not Started
Third Report | 2017-04-27 | 2017-05-01 | 5d |  | 0% | Not Started
Refine the changes | 2017-04-27 | 2017-05-01 | 5d |  | 0% | Not Started
Add the two reports together | 2017-04-27 | 2017-05-01 | 5d |  | 0% | Not Started
Demo 2 | 2017-04-22 | 2017-04-26 | 5d |  | 0% | Not Started
Product Brocure | 2017-04-22 | 2017-04-26 | 5d |  | 0% | Not Started
Prepare Slide Per Group | 2017-04-22 | 2017-04-26 | 5d |  | 0% | Not Started
Mock Demo | 2017-04-22 | 2017-04-26 | 5d |  | 0% | Not Started